## Sheet1
Column | What to Put | Column | What to Put
Risk ID | R-001 | Risk ID | R-002
Asset | Cameras feed | Asset | Desktop screen operating from VLC with no passwd
Risk Description | Unauthorized access to CCTV cameras leading to loss of surveillance and security monitoring | Risk Description | Unauthorized access to Desktops
Threat | External Hacker brute force | Threat | External attacker
Vulnerability | Weak passwords | Vulnerability | Unrestricted VLC access
Impact (1–5) | 5 | Impact (1–5) | 4
Likelihood (1–5) | 3 | Likelihood (1–5) | 3
Risk Score | 15 | Risk Score | 12
Risk Level | High | Risk Level | High
Existing Controls | Firewall, Password Policy | Existing Controls | Password Policy
ISO 27001 Control Reference | A.5.17 Authentication information | ISO 27001 Control Reference | A.5.15 Access control
Risk Owner | ICCC Manager | Risk Owner | ICCC Manager
Treatment Option | Mitigate | Treatment Option | Mitigate
Treatment Plan | Enforce alphanumaric passwds | Treatment Plan | Enforce alphanumaric passwds
Residual Risk | Medium | Residual Risk | Medium
Review Date | 2026-01-30 | Review Date | 2026-01-25
Column | What to Put
Risk ID | R-003
Asset | No MDM
Risk Description | Unauthorized MDM access to operations area
Threat | Sensitive fottage and documents get leaked
Vulnerability | No MDM policy enforced
Impact (1–5) | 4
Likelihood (1–5) | 3
Risk Score | 12
Risk Level | Medium
Existing Controls | MDM Policy
ISO 27001 Control Reference | A.6.3 Information security awareness / A.8.1 User endpoint devices
Risk Owner | ICCC Manager
Treatment Option | Mitigate
Treatment Plan | Enforce MDM policy
Residual Risk | low
Review Date | 2026-01-20

## Sheet2
Impact Scale
Score | Meaning
1 | Negligible
2 | Minor
3 | Moderate
4 | Major
5 | Critical
Likelihood Scale
Score | Meaning
1 | Rare
2 | Unlikely
3 | Possible
4 | Likely
5 | Almost Certain
Risk Score | Risk Level
1–5 | Low
6–12 | Medium
15–25 | High